## Slide 1: Accounting Engagement FDT Townsend & S&A Technologies Kick-Off Meeting

## Slide 2: Meeting Objectives
Team introduction
Project objectives & deliverables
Project structure overview
Expectations of management

## Slide 3: Project Objectives & Deliverables (Accounting)
Name | Description | Deliverable | Estimated Timeframe
Bank Reconciliations | Provide monthly bank reconciliations for all ULEC bank accounts, PayPal, Stripe, through December 31, 2019 in preparation for 2019 audit | Reconciliation Reports From QB | January 2020
Review Bank Account List | Recommend list of bank accounts to close and close them | Bank Account List Recommendation Report | February 2020
QuickBooks AR Module | Clean up old AR detail balance; prepare AR module to be utilized and to produce reports that management can use to make decisions | Updated AR Reports from QuickBooks (reports showing actual current balances) | January 2020
QuickBooks AP Module | Clean up old AP detail balance; prepare AP module to be utilized and to produce reports that management can use to make decisions | Updated AP Reports from QuickBooks (reports showing actual current balances) | January 2020

## Slide 4: Project Objectives & Deliverables (Accounting) Continue…
Name | Description | Deliverable | Estimated Timeframe
Chart of Accounts Review | Review chart of accounts to remove unnecessary accounts and remove them | New Chart of Accounts Report | February 2020
Moving Real Estate Activities (in QuickBooks) | Move real estate activities currently in one class to the Opportunity Corp, in a separate QuickBooks file. | List of Real Estate Adjusting Journal Entries & Updated Balance Sheet | February 2020

## Slide 5: Project Objectives & Deliverables (Administrative)
Name | Description | Deliverable | Estimated Timeframe
Processes Automation & Improvement | Prepare specific recommendations to improve accounting procedures by utilizing and implementing available technology for bill payment, recording credit card transactions using the QuickBooks app, etc. Automate credit card process and check cutting and move to ACH process | New Standard Operating Procedures (SOP) | February 2020
Automation of Grant Reporting Process | Review current grant award documentation requirements to find efficient and effective ways to compile and deliver periodic grant reporting; automate the grant reporting process and invoicing to funders | New Standard Operating Procedures (SOP) | February 2020
QuickBooks Classes Review | Review classes and provide recommendations for improved reporting structure | New Recommended List of Classes to use | February 2020
Cost Allocation Methodology | Develop and implement cost effective allocations methodology for overhead costs; develop required tools to do so | New Standard Operating Procedures (SOP) | February 2020

## Slide 6: Project Structure Overview
Group | Area | Primary Team Members
1 | Accounting | Migdelis & Priyanka
2 | Administrative | Peter + Intuit Resources
Primary Contact:
Floyd D. Townsend

## Slide 7: Expectations of Management During Project
Availability for progress meetings and process walkthrough meetings
Request for documents and information
Approvals/sign offs

## Slide 8: Next Steps
Establish list of
  participants and their roles
Schedule Meeting to
  process walkthrough
  Collect existing documented procedure
  Establish list of procedures, sops and reports and grant requirements
    Input for exploration
  Establish regular status reporting to whom
  Establish save document exchange
  Propose list of bank accounts to close
  Explore new tools (Bill.com, QB App) and propose for approval