## Plan
Urban League of Essex County
Accounting Engagement Project
|  | 2019 |  |  |  | 2020
Item/Time | Group | Dec |  |  |  | Jan |  |  | Feb
General Activites |  | Get access to QB
Collect exsiting processes and procedures
Establish project board and approval process
Bank Reconciliation | 1 |  |  |  |  | Bank Reconciliation Report
Bank Account List Recommendation | 1
Present to Management
Approve by Management
Implement
Review
Approve Live
AR detail balance | 1 |  |  |  |  | Open Invoice Report (Old with red indications of errors and new without red indications)
AP detail balance | 1 |  |  |  |  | Payment Report (Old with red indications of errors and new without red indications)
Remove unnecessary accounts | 1
Present List to Management
Approve
Implement
Review
Approve Live
Reporting Structure Recommendation | 2 |  | Gather requirements
Analysis
Present new structure to Management
Implement new reports
Review
Go Live
Move real estate activities | 3
Accounting procedures | 2
Grant documentation requirements | 2 |  | Same as Reporting Structure
SOP | 2 |  |  |  | Present list of SOPs to Management
Allocations methodology | 4 |  |  |  | Present Allocation Keys
Approve allocation keys by Management
Implement reporting with allocation
Review
Go Live